## Slide 1: Internal Audit - Business Continuity Readiness
General Corporate Operations
January 22, 2026

## Slide 2: Executive Summary
Objectives
To evaluate business continuity (BCP) preparedness, recovery plans and testing for critical corporate functions.
Background
BCP covers IT, facilities, HR and finance continuity arrangements across primary and backup sites.
Scope
Review of plan completeness, recent exercises, and recovery time objective (RTO) alignment.

## Slide 3: Observation 1: Incomplete Recovery Plans
Issue: Departmental BCPs lacked RTO/RPO definitions and clear recovery roles for three critical processes.
Risk: Prolonged outage and inability to meet stakeholder obligations during disruption.
Risk Rating: FOR IMPROVEMENT
Recommendation: Define RTO/RPO for critical processes and assign named recovery owners.

## Slide 4: Observation 2: Limited Exercise Coverage
Issue: Annual BCP exercises excluded several corporate support functions; last full test was 18 months ago.
Risk: Unvalidated recovery procedures and false confidence in readiness.
Risk Rating: INADEQUATE
Recommendation: Establish a 12-month exercise cycle covering critical and support functions; document lessons learned.

## Slide 5: Recommendations Summary
Define RTO/RPO and assign recovery owners for critical processes.
Implement annual full-scale BCP exercises with all support functions.
Capture and remediate exercise findings in a remediation log.

## Slide 6: Management Action Plan
Action Item | Owner | Deadline
Define RTO/RPO for critical processes | BCP Lead | March 2026
Annual full-scale exercise schedule | BCP Coordinator | April 2026
Remediation tracking log | Risk Manager | Feb 2026