## Slide 1: Title Slide
Report: Legal Department Operations and Contract Lifecycle Management
Business Unit: Legal Affairs
Date: February 25, 2026

## Slide 2: Executive Summary
Objectives
To assess the efficiency of the contract drafting, approval, and storage process.
Background
The legal team processes over 150 contracts per month.
Scope
Review of master service agreements (MSAs) and non-disclosure agreements (NDAs) from 2025.

## Slide 3: Observation 1: Use of Outdated Contract Templates
Issue: Procurement teams are using 2021 templates that lack current indemnity clauses.
Risk: Increased legal exposure and unfavorable liability terms.
Risk Rating: INADEQUATE
Recommendation: Centralize all templates in a ‘Single Source of Truth’ portal.
Status: Open

## Slide 4: Observation 2: Missing Signature Authorizations
Issue: 5 sampled contracts were signed by managers exceeding their delegated financial authority.
Risk: Invalid contracts and breach of internal control policies.
Risk Rating: FOR IMPROVEMENT
Recommendation: Integrate the ‘Delegation of Authority’ (DoA) into the e-signature workflow.
Status: In Progress

## Slide 5: Recommendations Summary
Enforce use of the centralized Legal Portal for templates.
Audit signature levels in DocuSign quarterly.
Provide training on the updated DoA limits.

## Slide 6: Management Action Plan
Action Item | Owner | Deadline
Template Portal | Legal Ops Mgr | April 2026
DoA Integration | IT / Legal | May 2026
Staff Training | General Counsel | June 2026