## Slide 1: Title Slide
Report: Mergers and Acquisitions (M&A) Post-Integration Audit
Business Unit: Corporate Development
Date: April 10, 2026

## Slide 2: Executive Summary
Objectives
To assess the success of integrating ‘Acme Corp’ (acquired 2025) into corporate operations.
Background
The $10M acquisition was intended to consolidate back-office functions by Q1 2026.
Scope
Review of payroll migration, IT systems consolidation, and policy alignment.

## Slide 3: Observation 1: Fragmented ERP Systems
Issue: The acquired entity is still using its legacy ERP, causing manual data consolidation errors.
Risk: Financial reporting inaccuracies and loss of operational synergy.
Risk Rating: INADEQUATE
Recommendation: Accelerate the migration to the corporate ERP platform.
Status: In Progress

## Slide 4: Observation 2: Misaligned HR Policies
Issue: Acquired employees are still operating under different leave and bonus structures.
Risk: Internal friction, morale issues, and potential payroll non-compliance.
Risk Rating: FOR IMPROVEMENT
Recommendation: Harmonize all HR benefits and policies by the next fiscal year.
Status: Open

## Slide 5: Recommendations Summary
Finalize ERP data migration by Q3.
Conduct a ‘Day 100’ review with all acquired department heads.
Issue a unified Employee Handbook.

## Slide 6: Management Action Plan
Action Item | Owner | Deadline
ERP Migration | IT / Finance | September 2026
Policy Harmonization | HR Director | December 2026
Synergy Audit | M&A Lead | June 2026